## Hyper-V Prod
Hostname | IP Address | Role | FollowUps | VM | ASR Status | Status | CPU | Memory（G） | Disk（G） | OS | Monitor | Classifications | Container | Migration owner | Rating | Wave | APP owner | For Asia or China only | Performance Level | Comments
r4whvhp001 | 10.82.48.43 | HyperV host 1 | to be shutdown | No | #N/A | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*2 | 576 | Remote storage | Windows Server 2012 R2 Datacenter | EM7/SCOM | Physical Server | N/A | N/A |  |  | Windows team | N/A | Normal | Hypervisor migration is not necessary
r4whvhp002 | 10.82.48.45 | HyperV host 2 | to be shutdown | No | #N/A | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*2 | 576 | Remote storage | Windows Server 2012 R2 Datacenter | EM7/SCOM | Physical Server | N/A | N/A |  |  | Windows team | N/A | Normal | Hypervisor migration is not necessary
r4whvhp003 | 10.82.48.47 | HyperV host 3 | to be shutdown | No | #N/A | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*2 | 576 | Remote storage | Windows Server 2012 R2 Datacenter | EM7/SCOM | Physical Server | N/A | N/A |  |  | Windows team | N/A | Normal | Hypervisor migration is not necessary
r4whvhp004 | 10.82.48.49 | HyperV host 4 | to be shutdown | No | #N/A | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*2 | 576 | Remote storage | Windows Server 2012 R2 Datacenter | EM7/SCOM | Physical Server | N/A | N/A |  |  | Windows team | N/A | Normal | Hypervisor migration is not necessary
r4whvhp005 | 10.82.48.51 | HyperV host 5 | to be shutdown | No | #N/A | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*2 | 576 | Remote storage | Windows Server 2012 R2 Datacenter | EM7/SCOM | Physical Server | N/A | N/A |  |  | Windows team | N/A | Normal | Hypervisor migration is not necessary
r4whvhp006 | 10.82.48.53 | HyperV host 6 | to be shutdown | No | #N/A | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*2 | 576 | Remote storage | Windows Server 2012 R2 Datacenter | EM7/SCOM | Physical Server | N/A | N/A |  |  | Windows team | N/A | Normal | Hypervisor migration is not necessary
r4whvhp007 | 10.82.48.55 | HyperV host 7 | to be shutdown | No | #N/A | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*2 | 576 | Remote storage | Windows Server 2012 R2 Datacenter | EM7/SCOM | Physical Server | N/A | N/A |  |  | Windows team | N/A | Normal | Hypervisor migration is not necessary
r4whvhp008 | 10.82.48.65 | HyperV host 8 | to be shutdown | No | #N/A | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*2 | 576 | Remote storage | Windows Server 2012 R2 Datacenter | EM7/SCOM | Physical Server | N/A | N/A |  |  | Windows team | N/A | Normal | Hypervisor migration is not necessary
r4wclhp001 | 10.82.48.60 | HyperV Cluster name | to be shutdown | No | #N/A | Running |  |  | N/A | Windows Server 2012 R2 Datacenter | EM7/SCOM | SQL cluster name | N/A | N/A |  |  | Windows team | N/A | Normal | No migration needed for Virtual host name
r4wsqlp001 | 10.82.32.22 | SQL server 1 | to be migration | No | #N/A | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*2 | 576 | 278 | Windows Server 2012 R2 Standard | EM7/SCOM | Physical Server | SQL Bare Metal | Eric/All Windows Team | 5 |  | Lst-digitaltech.CognizantMsSQL.DBA | Asia | High in IO and throughput
r4wsqlp002 | 10.82.32.23 | SQL server 2 | to be migration | No | #N/A | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*2 | 576 | 278/1/1 | Windows Server 2012 R2 Standard | EM7/SCOM | Physical Server | SQL Bare Metal | Eric/All Windows Team | 5 |  | Lst-digitaltech.CognizantMsSQL.DBA | Asia | High in IO and throughput
r4wsqlp003 | 10.82.32.24 | SQL server 3 | to be migration | No | #N/A | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*2 | 576 | 278/1/1 | Windows Server 2012 R2 Standard | EM7/SCOM | Physical Server | SQL Bare Metal | Eric/All Windows Team | 5 |  | Lst-digitaltech.CognizantMsSQL.DBA | Asia | High in IO and throughput
r4wclsp001 | 10.82.32.25 | SQL cluster name | to be migration | Yes | #N/A | Running | N/A | N/A | N/A | Windows Server 2012 R2 Standard | EM7/SCOM | SQL cluster name | SQL Bare Metal | Eric/All Windows Team | 5 |  | Lst-digitaltech.CognizantMsSQL.DBA | N/A | Normal | Vname of the SQL cluster
R4WSQLP-BI | 10.82.32.26 | BI SQL instance | to be migration | Yes | #N/A | Running | N/A | N/A | N/A | Windows Server 2012 R2 Standard | EM7/SCOM | SQL instance | SQL Bare Metal | Eric/All Windows Team | 5 |  | Lst-digitaltech.CognizantMsSQL.DBA | N/A | Normal
R4WSQLP-ER | 10.82.32.27 | ER SQL instance | to be migration | Yes | #N/A | Running | N/A | N/A | N/A | Windows Server 2012 R2 Standard | EM7/SCOM | SQL instance | SQL Bare Metal | Eric/All Windows Team | 5 |  | Lst-digitaltech.CognizantMsSQL.DBA | N/A | Normal
R4WSQLP-IR | 10.82.32.28 | IR SQL instance | to be migration | Yes | #N/A | Running | N/A | N/A | N/A | Windows Server 2012 R2 Standard | EM7/SCOM | SQL instance | SQL Bare Metal | Eric/All Windows Team | 5 |  | Lst-digitaltech.CognizantMsSQL.DBA | N/A | Normal
R4WSQLP-XC | 10.82.32.29 | XCenter SQL instance | to be migration | Yes | #N/A | Running | N/A | N/A | N/A | Windows Server 2012 R2 Standard | EM7/SCOM | SQL instance | SQL Bare Metal | Eric/All Windows Team | 5 |  | Lst-digitaltech.CognizantMsSQL.DBA | N/A | Normal
HK-NHKP1WTFCC01 | 10.82.32.175 | NHK---Traffic Count System | to be migration | Yes | NotApplicable | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*4 | 8 | 80/200 | Windows Server 2012 R2 Standard | EM7/SCOM | NHK | NHK1 | Tim Wu | 1 |  | Tony.Wu@nike.com | Asia | Normal
Hongkong-SVR-56 | 10.82.32.178 | Share web portal | to be migration | Yes | NotApplicable | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*4 | 8 | 40/400 | Windows Server 2008 R2 Enterprise | EM7/SCOM | Share web portal | Share web portal | Rongwei | 2 |  | Johnny.chan@nike.com | Asia | Normal
Hongkong-SVR-90 | 10.82.32.181 | Mange--MFT platform | to be migration | Yes | NotApplicable | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*2 | 4 | 80/100/100/60 | Windows Server 2008 R2 Standard | EM7/SCOM | IMFT | IMFT | Tim Wu | 4 |  | Madge.Chen@nike.com | Asia | Normal
MAPCTXP1WXFM005 | 10.82.32.176 | Converse-Baymark APP Server | to be migration | Yes | NotApplicable | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*8 | 32 | 80/100 | Windows Server 2008 R2 Standard | EM7/SCOM | Converse | Converse Raymark | Tim Wu | 2 |  | Converse RayMark Team(Jacky.chen@converse.com) | China Only | High on CPU or memory
NKE-WIN-APP-D11 | 10.82.32.188 | JP Workflow QA server | to be migration | Yes | NotApplicable | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*2 | 4 | 80/200 | Windows Server 2012 R2 Standard | EM7/SCOM | JP Workflow | JP Workflow1 | David Yin | 1 |  | Shinya.Tokai@nike.com | Asia | Normal
NKE-WIN-APP-P32 | 10.82.32.189 | JP Workflow Production server | to be migration | Yes | NotApplicable | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*2 | 4 | 80/200 | Windows Server 2012 R2 Standard | EM7/SCOM | JP Workflow | JP Workflow2 | David Yin | 1 |  | Shinya.Tokai@nike.com | Asia | Normal
NKE-WIN-FNP-P43 | 10.82.32.180 | Batch jobs to update NHK and converse database | to be migration | Yes | NotApplicable | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*4 | 8 | 80/250 | Windows Server 2012 R2 Standard | EM7/SCOM | NHK | NHK2 | Tim Wu | 2 |  | Tony.Wu@nike.com | Asia | High in IO and throughput
NKE-WIN-SCM-P22 | 10.82.32.225 | SCCM-AHQ Primary Site Server | to be migration | Yes | NotApplicable | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*8 | 32 | 80 | Windows Server 2012 R2 Standard | EM7/SCOM | SCCM | SCCM | Yu Xun/Jim Wang | 4 |  | SCCM Team/Lst-CDT.Retail.SCCM@nike.com | Asia | Normal
NKE-WIN-SCM-P42 | 10.82.32.228 | SCCM-AS1 Secondary Site | to be migration | Yes | NotApplicable | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*8 | 16 | 80 | Windows Server 2012 R2 Standard | EM7/SCOM | SCCM | SCCM | Yu Xun/Jim Wang | 4 |  | SCCM Team/Lst-CDT.Retail.SCCM@nike.com | Asia | Normal
NKE-WIN-SCM-P43 | 10.82.32.229 | SCCM-AS2 Secondary Site | to be migration | Yes | NotApplicable | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*8 | 16 | 80 | Windows Server 2012 R2 Standard | EM7/SCOM | SCCM | SCCM | Yu Xun/Jim Wang | 4 |  | SCCM Team/Lst-CDT.Retail.SCCM@nike.com | Asia | Normal
NKE-WIN-SQL-P46 | 10.82.32.179 | Share DB server（hongkong-svr-56's DB ） | to be migration | Yes | NotApplicable | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*6 | 29 | 80/380/240/400 | Windows Server 2012 R2 Standard | EM7/SCOM | Share web portal | Share web portal | Rongwei | 2 |  | Johnny.chan@nike.com | Asia | High in IO and throughput
R4LORACLE001 | 10.82.32.190 | oracle db | to be confimed | Yes | NotApplicable | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*2 | 8 | 256 | Red Hat Enterprise Linux 6 | EM7/SCOM | oracle db | Oracle DB | Shayne/Luo Yi | 3 |  | YoungKwon Jun and Semin Lee | To be confirmed | To be confirmed | Handled by Linux team
R4LORACLE002 | 10.82.32.191 | oracle db | to be confimed | Yes | NotApplicable | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*2 | 8 | 256 | Red Hat Enterprise Linux 6 | EM7/SCOM | oracle db | Oracle DB | Shayne/Luo Yi | 3 |  | YoungKwon Jun and Semin Lee | To be confirmed | To be confirmed | Handled by Linux team
R4LORACLE003 | 10.82.32.192 | oracle db | to be confimed | Yes | NotApplicable | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*4 | 16 | 256 | Red Hat Enterprise Linux 6 | EM7/SCOM | oracle db | Oracle DB | Shayne/Luo Yi | 3 |  | YoungKwon Jun and Semin Lee | To be confirmed | To be confirmed | Handled by Linux team
R4WAPPP001 | 10.82.32.40 | Application Server (GSS)----CORP | to be migration | Yes | Normal | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*2 | 8 | 80/150 | Windows Server 2012 R2 Standard | EM7/SCOM | AP Application Server | Application Server (GSS)----CORP | Tim Ni | 1 |  | Lst-NIKE.RETAIL.WHQ.APP | Asia | Normal
R4WAPPP002 | 10.82.32.41 | Application Server (GSS)----ER | to be migration | Yes | Normal | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*2 | 8 | 80/150 | Windows Server 2012 R2 Standard | EM7/SCOM | AP Application Server | Application Server (GSS)----ER | Rongwei | 2 |  | Lst-NIKE.RETAIL.WHQ.APP | Asia | Normal
R4WAPPP003 | 10.82.32.42 | Application Server (GSS)----Reporting | to be migration | Yes | Normal | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*1 | 8 | 80/40 | Windows Server 2012 R2 Standard | EM7/SCOM | AP Application Server | Application Server (GSS)----Reporting | Rongwei | 2 |  | Lst-NIKE.RETAIL.WHQ.APP Lst-NIKE.RETAIL.WHQ.GB2.L3 | Asia | Normal
R4WAPPP004 | 10.82.32.43 | Application Server (GSS)----External Interface server (EIR) | to be migration | Yes | Normal | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*2 | 8 | 80/150 | Windows Server 2012 R2 Standard | EM7/SCOM | AP Application Server | Application Server (GSS)----External Interface server (EIR) | Tim Ni | 1 |  | Lst-NIKE.RETAIL.WHQ.APP | Asia | Normal
R4WAPPP005 | 10.82.32.44 | Application Server (GSS)----DCN Tool | to be migration | Yes | Critical | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*2 | 8 | 80/100 | Windows Server 2012 R2 Standard | EM7/SCOM | AP Application Server | Application Server (GSS)----DCN Tool | Tim Ni | 1 |  | Lst-NIKE.RETAIL.WHQ.APP Lst-NIKE.RETAIL.WHQ.GB2.L3 | Asia | Normal
R4WAPPP010 | 10.82.32.49 | Application Server (GSS)----IIS(Training Website) | to be migration | Yes | Normal | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*1 | 8 | 80/40 | Windows Server 2012 R2 Standard | EM7/SCOM | AP Application Server | Application Server (GSS)----IIS(Training Website) | Tim Ni | 1 |  | Lst-NIKE.RETAIL.WHQ.APP | Asia | Normal
R4WAPPP011 | 10.82.32.50 | Application Server (GSS)----IIS(Training Website) | to be migration | Yes | Normal | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*1 | 8 | 80/40 | Windows Server 2012 R2 Standard | EM7/SCOM | AP Application Server | Application Server (GSS)----IIS(Training Website) | Tim Ni | 1 |  | Lst-NIKE.RETAIL.WHQ.APP | Asia | Normal
R4WAPPP012 | 10.82.32.51 | Application Server (GSS)----IIS (WEB EJ) | to be migration | Yes | Normal | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*1 | 8 | 80/40 | Windows Server 2012 R2 Standard | EM7/SCOM | AP Application Server | Application Server (GSS)----IIS (WEB EJ) | George Liu | 2 |  | Lst-NIKE.RETAIL.WHQ.APP | Asia | Normal
R4WAPPP013 | 10.82.32.52 | Application Server (GSS)----IIS (WEB EJ) | to be migration | Yes | Normal | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*1 | 8 | 80/40 | Windows Server 2012 R2 Standard | EM7/SCOM | AP Application Server | Application Server (GSS)----IIS (WEB EJ) | George Liu | 2 |  | Lst-NIKE.RETAIL.WHQ.APP | Asia | Normal
R4WAPPP014 | 10.82.32.53 | Application Server (GSS)----Misc Apps | to be migration | Yes | Normal | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*1 | 8 | 80/100 | Windows Server 2012 R2 Standard | EM7/SCOM | AP Application Server | Application Server (GSS)----Misc Apps | Tim Ni | 1 |  | Lst-NIKE.RETAIL.WHQ.APP | Asia | Normal
R4WAPPP015 | 10.82.32.54 | Application Server (GSS)----EJ | to be migration | Yes | Normal | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*2 | 8 | 80/150 | Windows Server 2012 R2 Standard | EM7/SCOM | AP Application Server | Application Server (GSS)----EJ | Tim Ni | 1 |  | Lst-NIKE.RETAIL.WHQ.APP | Asia | Normal
R4WAPPP016 | 10.82.32.55 | Application Server (GSS)----MSMQ | to be migration | Yes | Normal | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*2 | 8 | 80/40 | Windows Server 2012 R2 Standard | EM7/SCOM | AP Application Server | Application Server (GSS)----MSMQ | George Liu | 2 |  | Lst-NIKE.RETAIL.WHQ.APP | Asia | Normal
R4WAPPP017 | 10.82.32.56 | Application Server (GSS)----MSMQ | to be migration | Yes | Normal | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*2 | 8 | 80/40 | Windows Server 2012 R2 Standard | EM7/SCOM | AP Application Server | Application Server (GSS)----MSMQ | George Liu | 2 |  | Lst-NIKE.RETAIL.WHQ.APP | Asia | Normal
R4WAPPP018 | 10.82.32.57 | Application Server (GSS)----MSMQ | to be migration | Yes | Normal | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*2 | 8 | 80/40 | Windows Server 2012 R2 Standard | EM7/SCOM | AP Application Server | Application Server (GSS)----MSMQ | Rongwei | 2 |  | Lst-NIKE.RETAIL.WHQ.APP | Asia | Normal
R4WAPPP019 | 10.82.32.58 | Application Server (GSS)----MSMQ | to be migration | Yes | Normal | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*2 | 8 | 80/40 | Windows Server 2012 R2 Standard | EM7/SCOM | AP Application Server | Application Server (GSS)----MSMQ | David Yin | 2 |  | Lst-NIKE.RETAIL.WHQ.APP | Asia | Normal
R4WAPPP022 | 10.82.32.61 | Application Server (GSS)----RemoteWare | to be migration | Yes | Normal | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*2 | 8 | 80/80 | Windows Server 2012 R2 Standard | EM7/SCOM | AP Application Server | Application Server (GSS)----RemoteWare | Tim Ni | 1 |  | Lst-NIKE.RETAIL.WHQ.APP Lst-NIKE.RETAIL.WHQ.GB2.L3 | Asia | Normal
R4WAPPP023 | 10.82.32.62 | Application Server (GSS)----RemoteWare | to be migration | Yes | Normal | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*2 | 8 | 80/80 | Windows Server 2012 R2 Standard | EM7/SCOM | AP Application Server | Application Server (GSS)----RemoteWare | Tim Ni | 1 |  | Lst-NIKE.RETAIL.WHQ.APP Lst-NIKE.RETAIL.WHQ.GB2.L3 | Asia | Normal
R4WAPPP024 | 10.82.32.63 | Application Server (China_BI) | to be migration | Yes | NotApplicable | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*16 | 64 | 60 | Windows Server 2012 R2 Standard | EM7/SCOM | China_BI | China_BI | Eric/George Liu | 5 |  | Lst-GC.Retail.MerchBI.Support@nike.com | China Only | CPU Memory and Disk
R4WAPPP025 | 10.82.32.64 | Application Server (China_BI) | to be migration | Yes | Critical | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*8 | 64 | 60 | Windows Server 2012 R2 Standard | EM7/SCOM | China_BI | China_BI | Eric/George Liu | 5 |  | Lst-GC.Retail.MerchBI.Support@nike.com | China Only | CPU Memory and Disk
R4WAPPP026 | 10.82.32.65 | Application Server (China_BI) | to be migration | Yes | NotApplicable | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*8 | 64 | 60 | Windows Server 2012 R2 Standard | EM7/SCOM | China_BI | China_BI | Eric/George Liu | 5 |  | Lst-GC.Retail.MerchBI.Support@nike.com | China Only | CPU Memory and Disk
R4WAPPP027 | 10.82.32.66 | Application Server (China_BI) | to be migration | Yes | Normal | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*16 | 32 | 80 | Windows Server 2012 R2 Standard | EM7/SCOM | China_BI | China_BI | Eric/George Liu | 5 |  | Lst-GC.Retail.MerchBI.Support@nike.com | China Only | CPU Memory and Disk
R4WAPPP028 | 10.82.32.67 | Application Server (China_BI) | to be migration | Yes | Normal | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*2 | 8 | 60 | Windows Server 2012 R2 Standard | EM7/SCOM | China_BI | China_BI | Eric/George Liu | 5 |  | Lst-GC.Retail.MerchBI.Support@nike.com | China Only | Normal
R4WAPPP029 | 10.82.32.68 | Application Server (China_BI) | to be migration | Yes | Normal | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*8 | 12 | 80/500/500 | Windows Server 2012 R2 Standard | EM7/SCOM | China_BI | China_BI | Eric/George Liu | 5 |  | Lst-GC.Retail.MerchBI.Support@nike.com | China Only | Normal
R4WAPPP030 | 10.82.32.69 | Application Server (China_Raymark) | to be migration | Yes | Normal | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*2 | 4 | 60 | Windows Server 2012 R2 Standard | EM7/SCOM | China_Raymark | China_Raymark | David Yin | 2 |  | ailsa.xue@nike.com | China Only | Normal
R4WAPPP031 | 10.82.32.70 | Application Server (China_Raymark) | to be migration | Yes | NotApplicable | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*4 | 32 | 60 | Windows Server 2012 R2 Standard | EM7/SCOM | China_Raymark | China_Raymark | David Yin | 2 |  | ailsa.xue@nike.com | China Only | Normal
R4WAPPP032 | 10.82.32.71 | Application Server (China_SFTP) | to be migration | Yes | Normal | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*1 | 4 | 80 | Windows Server 2012 R2 Standard | EM7/SCOM | SFTP | SFTP | Tim Wu | 4 |  | ailsa.xue@nike.com | China Only | Normal
R4WAPPP033 | 10.82.32.72 | Application Server (China_WinnerTrafficCount) | to be migration | Yes | Normal | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*4 | 16 | 60 | Windows Server 2012 R2 Standard | EM7/SCOM | TrafficCount | TrafficCount | David Yin | 1 |  | ailsa.xue@nike.com | China Only | Normal
R4WAPPP034 | 10.82.32.73 | Application Server (Japan_TrafficCount) | to be migration | Yes | Normal | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*4 | 4 | 80/100/40 | Windows Server 2012 R2 Standard | EM7/SCOM | Japan Application | Japan Application | Shinya/David Yin | 2 |  | Shinya.Tokai@nike.com | Asia | Normal
R4WAPPP035 | 10.82.32.74 | Application Server (Japan_Oracle)（to be decommission） | to be migration | Yes | #N/A | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*2 | 4 | 40 | Windows Server 2012 R2 Standard | EM7/SCOM | TBD | TBD | TBD | TBD | TBD | Lst-digitaltech.CognizantMsSQL.DBA | Asia | Normal | Confirm with Shinya san
R4WAPPP036 | 10.82.32.75 | Application Server (Japan_AthleteAttendance) | to be migration | Yes | Normal | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*2 | 8 | 60/200 | Windows Server 2012 R2 Standard | EM7/SCOM | Japan Application | Japan Application | Shinya/David Yin | 2 |  | Shinya.Tokai@nike.com | Asia | Normal
R4WAPPP037 | 10.82.32.76 | Application Server (Japan_AthleteAttendance) | to be migration | Yes | Normal | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*4 | 8 | 60/200 | Windows Server 2012 R2 Standard | EM7/SCOM | Japan Application | Japan Application | Shinya/David Yin | 2 |  | Shinya.Tokai@nike.com | Asia | Normal
R4WAPPP038 | 10.82.32.77 | Application Server (Japan_WorkSchedule) | to be migration | Yes | Normal | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*4 | 4 | 80/40 | Windows Server 2012 R2 Standard | EM7/SCOM | Japan Application | Japan Application | Shinya/David Yin | 2 |  | Shinya.Tokai@nike.com | Asia | Normal
R4WAPPP039 | 10.82.32.78 | Application Server (Japan) | to be migration | Yes | Warning | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*1 | 2 | 36/100 | Windows Server 2012 R2 Standard | EM7/SCOM | Japan Application | Japan Application | Shinya/David Yin | 2 |  | Shinya.Tokai@nike.com | Asia | Normal
R4WAPPP040 | 10.82.32.79 | Application Server (GSS)----MSMQ | to be migration | Yes | Normal | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*2 | 8 | 80/80 | Windows Server 2012 R2 Standard | EM7/SCOM | AP Application Server | Application Server (GSS)----MSMQ | Jim Wang | 2 |  | Lst-NIKE.RETAIL.WHQ.APP | Asia | Normal
R4WAPPP041 | 10.82.32.80 | GB2 XCenter server 1（to be decommission） | to be shutdown | Yes | Normal | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*4 | 32 | 80/300 | Windows Server 2012 R2 Standard | EM7/SCOM | XCenter | Application Server (GSS)----Relate | Rongwei | 2 |  | Lst-NIKE.RETAIL.WHQ.APP Lst-NIKE.RETAIL.WHQ.GB2.L3 | China Only | High on CPU or memory | To be decommissioned before Oct
R4WAPPP042 | 10.82.32.81 | GB2 XCenter server 2（to be decommission） | to be shutdown | Yes | Critical | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*4 | 32 | 80/300 | Windows Server 2012 R2 Standard | EM7/SCOM | XCenter | Application Server (GSS)----Relate | Rongwei | 2 |  | Lst-NIKE.RETAIL.WHQ.APP Lst-NIKE.RETAIL.WHQ.GB2.L3 | China Only | High on CPU or memory | To be decommissioned before Oct
R4WAPPP043 | 10.82.32.82 | GB2 XCenter server 3 （to be decommission） | to be shutdown | Yes | Critical | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*4 | 32 | 80/300 | Windows Server 2012 R2 Standard | EM7/SCOM | XCenter | Application Server (GSS)----MSMQ | Jim Wang | 2 |  | Lst-NIKE.RETAIL.WHQ.APP Lst-NIKE.RETAIL.WHQ.GB2.L3 | China Only | High on CPU or memory | To be decommissioned before Oct
R4WAPPP044 | 10.82.32.83 | Application Server (GSS)----Relate | to be migration | Yes | Normal | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*4 | 32 | 80/100 | Windows Server 2012 R2 Standard | EM7/SCOM | AP Application Server | Application Server (GSS)----Relate | George Liu | 2 |  | Lst-NIKE.RETAIL.WHQ.APP Lst-NIKE.RETAIL.WHQ.GB2.L3 | Asia | Normal
R4WAPPP045 | 10.82.32.84 | Application Server (GSS)----Relate | to be migration | Yes | Normal | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*4 | 32 | 80/100 | Windows Server 2012 R2 Standard | EM7/SCOM | AP Application Server | Application Server (GSS)----Relate | Tim Ni | 2 |  | Lst-NIKE.RETAIL.WHQ.APP Lst-NIKE.RETAIL.WHQ.GB2.L3 | Asia | Normal
R4WAPPP046 | 10.82.32.87 | customer service web site | to be migration | Yes | Normal | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*2 | 8 | 80/400 | Windows Server 2012 R2 Standard | EM7/SCOM | Web Site | Customized web site | Rongwei | 1 |  | Lin, Lisa <Lisa.Lin@nike.com> | Asia | China Only
R4WAPPP047 | 10.82.32.88 | to be shutdown | to be shutdown | Yes | Normal | Stopped | Intel Xeon CPU E5-2699 V3 2.30GHz*2 | 4 | 100/400 | Windows Server 2012 R2 Standard | EM7/SCOM |  | N/A | N/A |  |  | TBC | TBC | TBC
R4WAPPP048 | 10.82.32.89 | new monitoring tool box | to be migration | Yes | Normal | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*2 | 4 | 80/80 | Windows Server 2012 R2 Standard | EM7/SCOM | TBD | TBD | TBD | TBD | TBD | To be confirmed | To be confirmed | To be confirmed | Shutdown to find out the owner
R4WAPPP049 | 10.82.32.90 | ServiceNow mid server | to be migration | Yes | Normal | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*4 | 16 | 80 | Windows Server 2012 R2 Standard | EM7/SCOM | Service Now | Service Now Mid server | Rongwei | 1 |  | Jon.Beck@nike.com | Asia | Normal
R4WAPPP050 | 10.82.32.91 | To be confirmed | to be shutdown | Yes | Normal | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*4 | 16 | 80 | Windows Server 2012 R2 Standard | EM7/SCOM |  | N/A | N/A |  |  | To be confirmed | To be confirmed | To be confirmed | checking with Cordeiro, William
R4WAPPP051 | 10.82.32.92 | To be confirmed | to be shutdown | Yes | Normal | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*2 | 4 | 80 | Windows Server 2012 R2 Standard | EM7/SCOM |  | N/A | N/A |  |  | To be confirmed | To be confirmed | To be confirmed | checking with Cordeiro, William
R4WAPPP052 | 10.82.32.93 | wholesale BI(NKE-WIN-TBL-D02) | to be migration | Yes | Critical | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*8 | 64 | 80/500/500 | Windows Server 2012 R2 Standard | EM7/SCOM | wholesale BI | wholesale BI | Eric/Rongwei | 5 |  | Tina.Li2@nike.com | China Only | CPU Memory and Disk
R4WAPPP053 | 10.82.32.94 | wholesale BI(NKE-WIN-DMA-P06) | to be migration | Yes | Critical | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*8 | 12 | 80/1023/500 | Windows Server 2012 R2 Standard | EM7/SCOM | wholesale BI | wholesale BI | Eric/Rongwei | 5 |  | Tina.Li2@nike.com | China Only | CPU Memory and Disk
R4WAPPP054 | 10.82.32.95 | wholesale BI(NKE-WIN-COG-P22) | to be migration | Yes | Critical | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*8 | 64 | 80/500/500 | Windows Server 2012 R2 Standard | EM7/SCOM | wholesale BI | wholesale BI | Eric/Rongwei | 5 |  | Tina.Li2@nike.com | China Only | CPU Memory and Disk
R4WAPPP055 | 10.82.32.96 | wholesale BI(NKE-WIN-DMA-Q03) | to be migration | Yes | NotApplicable | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*2 | 64 | 80/1000/500/1000 | Windows Server 2012 R2 Standard | EM7/SCOM | wholesale BI | wholesale BI | Eric/Rongwei | 5 |  | Tina.Li2@nike.com | China Only | CPU Memory and Disk
R4WAPPP056 | 10.82.32.97 | wholesale BI(NKE-WIN-SQL-PB7) | to be migration | Yes | Critical | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*2 | 32 | 80/500/500 | Windows Server 2012 R2 Standard | EM7/SCOM | wholesale BI | wholesale BI | Eric/Rongwei | 5 |  | Tina.Li2@nike.com | China Only | CPU Memory and Disk
R4WAPPP057 | 10.82.32.98 | wholesale BI(NKE-WIN-DMA-P07) | to be migration | Yes | NotApplicable | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*16 | 64 | 80/1000/500/1000/1000/1000/1000/1000/3072 | Windows Server 2012 R2 Standard | EM7/SCOM | wholesale BI | wholesale BI | Eric/Rongwei | 5 |  | Tina.Li2@nike.com | China Only | CPU Memory and Disk
R4WAPPP058 | 10.82.32.99 | Application Server (GSS)----MSMQ | to be migration | Yes | Normal | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*2 | 4 | 80/40 | Windows Server 2012 R2 Standard | EM7/SCOM | AP Application Server | Application Server (GSS)----MSMQ | David Yin | 2 |  | Lst-NIKE.RETAIL.WHQ.APP | Asia | China Only
R4WAPPP059 | 10.82.32.103 | wholesale BI(NKE-WIN-SQL-PD4) | to be migration | Yes | NotApplicable | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*16 | 64 | 80/1000/500/1000/1000/1000/1023/2048 | Windows Server 2012 R2 Standard | EM7/SCOM | wholesale BI | wholesale BI | Eric/Rongwei | 5 |  | Tina.Li2@nike.com | China Only | CPU Memory and Disk
R4WAPPP061 | 10.82.32.105 | NHK | to be migration | Yes | Normal | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*12 | 32 | 80/200/500/20/10/20/10/10/5/10/5 | Windows Server 2012 R2 Standard | EM7/SCOM | NHK | NHK3 | Tim Wu | 1 |  | Tony.Wu@nike.com | Asia | High on CPU or memory
R4WAPPP062 | 10.82.32.106 | blank Server , to be shutdown | to be shutdown | Yes | Normal | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*1 | 4 | 80 | N/A | EM7/SCOM | N/A | N/A | N/A |  |  | N/A | N/A | Normal | To be decommissioned
R4WAPPP063 | 10.82.32.107 | blank Server , to be shutdown | to be shutdown | Yes | Normal | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*1 | 4 | 80 | N/A | EM7/SCOM | N/A | N/A | N/A |  |  | N/A | N/A | Normal | To be decommissioned
R4WAPPP064 | 10.82.32.108 | blank Server , to be shutdown | to be shutdown | Yes | Normal | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*1 | 4 | 80 | N/A | EM7/SCOM | N/A | N/A | N/A |  |  | N/A | N/A | Normal | To be decommissioned
R4WAPPP065 | 10.82.32.109 | blank Server , to be shutdown | to be shutdown | Yes | Normal | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*1 | 4 | 80 | N/A | EM7/SCOM | N/A | N/A | N/A |  |  | N/A | N/A | Normal | To be decommissioned
R4WAPPP073 | 10.82.32.117 | blank Server , to be shutdown | to be shutdown | Yes | Normal | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*1 | 4 | 80 | N/A | EM7/SCOM | N/A | N/A | N/A |  |  | N/A | N/A | Normal | To be decommissioned
R4WAPPP074 | 10.82.32.118 | blank Server , to be shutdown | to be shutdown | Yes | Normal | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*1 | 4 | 80 | N/A | EM7/SCOM | N/A | N/A | N/A |  |  | N/A | N/A | Normal | To be decommissioned
R4WAPPP075 | 10.82.32.119 | blank Server , to be shutdown | to be shutdown | Yes | Normal | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*1 | 4 | 80 | N/A | EM7/SCOM | N/A | N/A | N/A |  |  | N/A | N/A | Normal | To be decommissioned
R4WAPPP076 | 10.82.32.120 | blank Server , to be shutdown | to be shutdown | Yes | Normal | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*1 | 4 | 80 | N/A | EM7/SCOM | N/A | N/A | N/A |  |  | N/A | N/A | Normal | To be decommissioned
R4WAPPP080 | 10.82.32.124 | DB Monitor spotlight | to be migration | Yes | Normal | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*4 | 16 | 80/200/200/100/80/50 | Windows Server 2012 R2 Standard | EM7/SCOM | DB Monitor | DB Monitor | Tim Ni | 1 |  | GCHQ DB Team | China Only | Normal
R4WAPPP082 | 10.82.32.126 | Converse B2B Portal/Order Capture | to be migration | Yes | Normal | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*2 | 2 | 80/100 | Windows Server 2012 R2 Standard | EM7/SCOM | Converse | Converse BI | Tim Wu | 2 |  | Stanly.Wang@converse.com | China Only | Normal | SINIAPP1WDMZ04 in DMZ
R4WAPPP083 | 10.82.32.127 | Converse BI Database purpose | to be migration | Yes | Normal | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*4 | 64 | 80/500/500 | Windows Server 2012 R2 Standard | EM7/SCOM | Converse | Converse BI | Tim Wu | 2 |  | Stanly.Wang@converse.com | China Only | High on CPU or memory | SINIAPP1WDMZ04 in DMZ
R4WAPPP084 | 10.82.32.128 | Converse Xpert, XEIS | to be migration | Yes | Normal | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*4 | 32 | 80/100 | Windows Server 2012 R2 Standard | EM7/SCOM | Converse | Converse1 | Tim Wu | 1 |  | Converse RayMark Team(Jacky.chen@converse.com) | China Only | Normal
R4WAPPP085 | 10.82.32.129 | Converse Xpert, XEIS | to be migration | Yes | NotApplicable | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*8 | 32 | 80/1000/500 | Windows Server 2012 R2 Standard | EM7/SCOM | Converse | Converse2 | Tim Wu | 1 |  | Converse RayMark Team(Jacky.chen@converse.com) | China Only | Normal
R4WAPPP086 | 10.82.32.130 | Region file sharing | to be migration | Yes | Normal | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*8 | 8 | 80/600 | Windows Server 2012 R2 Standard | EM7/SCOM | Share folder | Share folder | George Liu | 1 |  | Windows team | China Only | Normal
R4WAPPP087 | 10.82.32.131 | Converse B2B Application internet interface | to be migration | Yes | Normal | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*2 | 12 | 80/200 | Windows Server 2012 R2 Standard | EM7/SCOM | Converse | Converse BI | Tim Wu | 2 |  | Stanly.Wang@converse.com | China Only | Normal | SINIAPP1WDMZ04 in DMZ
R4WAPPP088 | 10.82.32.132 | Confluence Server | to be migration | Yes | Normal | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*4 | 32 | 80/1000 | Windows Server 2012 R2 Standard | EM7/SCOM | Confluence Server | Confluence Server | Jim Wang | 1 |  | Adam.Tang2@nike.com | China Only | Normal
R4WAPPP090 | 10.82.32.134 | SolarWinds NPM server | to be migration | Yes | NotApplicable | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*4 | 32 | 80/200 | Windows Server 2012 R2 Standard | EM7/SCOM | SolarWinds | SolarWinds | MaoYan/Tim Ni | 2 |  | Steve.Johnston@nike.com/Valjean.Clark@nike.com | Asia | High on CPU or memory
R4WAPPP091 | 10.82.32.135 | SolarWinds NTA server | to be migration | Yes | NotApplicable | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*8 | 64 | 80/500 | Windows Server 2012 R2 Standard | EM7/SCOM | SolarWinds | SolarWinds | MaoYan/Tim Ni | 2 |  | Steve.Johnston@nike.com/Valjean.Clark@nike.com | Asia | High on CPU or memory
R4WAPPP092(SINMONP1WSQL001) | 10.82.32.136 | SolarWinds SQL server | to be migration | Yes | #N/A | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*8 | 64 | 80/500/1/400 | Windows Server 2012 R2 Standard | EM7/SCOM | SolarWinds | SolarWinds | MaoYan/Tim Ni | 2 |  | Steve.Johnston@nike.com/Valjean.Clark@nike.com | Asia | High on CPU or memory | VMM name is R4WAPPP092
R4WAPPP094 | 10.82.32.138 | Prod for cognos portal | to be migration | Yes | NotApplicable | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*8 | 64 | 80/500/500 | Windows Server 2012 R2 Standard | EM7/SCOM | cognos portal | cognos portal | Jim Wang | 3 |  | Mark.Zhou@nike.com | Asia | High on CPU or memory
R4WAPPP095 | 10.82.32.139 | IDP/VIP Portal/Giveaway/Format Conversion | to be migration | Yes | NotApplicable | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*1 | 4 | 80/100 | Windows Server 2012 R2 Standard | EM7/SCOM | NHK | NHK4 | Tim Wu | 1 |  | Tony.Wu@nike.com | Asia | Normal
R4WAPPP096 | 10.82.32.140 | NIKE BI | to be migration | Yes | NotApplicable | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*1 | 4 | 80/200/200 | Windows Server 2012 R2 Standard | EM7/SCOM | NIKE BI | NIKE BI | Jim Wang | 3 |  | Mark.Zhou@nike.com | Asia | Normal
SINADSP1WWNS001 | 10.82.32.141 | APAC WINS Server | to be confimed | Yes | #N/A | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*1 | 4 | 80 | Windows Server 2012 R2 Standard | EM7/SCOM | WINS | N/A | N/A |  |  | AD & DDI Team/Terry.Bingham@nike.com | Asia | Normal | VMM name is R4WAPPP097
R4WAPPP098 | 10.82.32.142 | Tim(NHK)/NKE-WIN-DMA-P19 | to be migration | Yes | NotApplicable | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*1 | 4 | 80/200/400 | Windows Server 2012 R2 Standard | EM7/SCOM | NHK | NHK5 | Tim Wu | 1 |  | Tony.Wu@nike.com | Asia | Normal
R4WAPPP101 | 10.82.32.145 | Tim(Citrix test server in SGDC) to be shutdown | to be shutdown | Yes | NotApplicable | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*1 | 4 | 80/100 | Windows Server 2012 R2 Standard | EM7/SCOM |  | N/A | N/A |  |  | N/A | N/A | Normal | To be decommissioned
R4WAPPP102 | 10.82.32.146 | Tim(Citrix test server in SGDC) to be shutdown | to be shutdown | Yes | NotApplicable | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*1 | 4 | 80/100 | Windows Server 2012 R2 Standard | EM7/SCOM |  | N/A | N/A |  |  | N/A | N/A | Normal | To be decommissioned
R4WAPPP103 | 10.82.32.147 | Jim(temporary)to be shutdown | to be shutdown | Yes | NotApplicable | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*2 | 8 | 80 | Windows Server 2012 R2 Standard | EM7/SCOM |  | N/A | N/A |  |  | N/A | N/A | Normal | To be decommissioned
R4WAPPP105 | 10.82.32.149 | to be shutdown | to be shutdown | Yes | NotApplicable | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*1 | 4 | 80/1000 | Windows Server 2012 R2 Standard | EM7/SCOM |  | N/A | N/A |  |  | N/A | N/A | Normal | To be decommissioned
R4WAPPP106 | 10.82.32.150 | SolarWinds | to be migration | Yes | NotApplicable | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*4 | 16 | 80/150 | Windows Server 2012 R2 Standard | EM7/SCOM | SolarWinds | SolarWinds | MaoYan/Tim Ni | 2 |  | N/A | Asia | High on CPU or memory
R4WAPPP108 | 10.82.32.152 | blank Server , to be shutdown | to be shutdown | Yes | NotApplicable | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*1 | 4 | 80 | Windows Server 2012 R2 Standard | EM7/SCOM |  | N/A | N/A |  |  | N/A | N/A | Normal | To be decommissioned
R4WAPPP109 | 10.82.32.153 | blank Server , to be shutdown | to be shutdown | Yes | NotApplicable | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*1 | 4 | 80 | Windows Server 2012 R2 Standard | EM7/SCOM |  | N/A | N/A |  |  | N/A | N/A | Normal | To be decommissioned
R4WAPPP110 | 10.82.32.154 | blank Server , to be shutdown | to be shutdown | Yes | NotApplicable | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*1 | 4 | 80 | Windows Server 2012 R2 Standard | EM7/SCOM |  | N/A | N/A |  |  | N/A | N/A | Normal | To be decommissioned
R4WAPPP111 | 10.82.32.155 | blank Server , to be shutdown | to be shutdown | Yes | NotApplicable | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*1 | 4 | 80 | Windows Server 2012 R2 Standard | EM7/SCOM |  | N/A | N/A |  |  | N/A | N/A | Normal | To be decommissioned
R4WAPPP115 |  | blank Server , to be shutdown | to be shutdown | Yes | NotApplicable | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*1 | 4 | 80 | Windows Server 2012 R2 Standard | EM7/SCOM |  | N/A | N/A |  |  | N/A | N/A | Normal | To be decommissioned
R4WAPPP128 | 10.82.32.172 | blank Server , to be shutdown | to be shutdown | Yes | NotApplicable | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*8 | 12 | 80 | Windows Server 2012 R2 Standard | EM7/SCOM |  | N/A | N/A |  |  | N/A | N/A | Normal | To be decommissioned
R4WAPPP129 | 10.82.32.173 | blank Server , to be shutdown | to be shutdown | Yes | NotApplicable | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*8 | 12 | 80 | Windows Server 2012 R2 Standard | EM7/SCOM |  | N/A | N/A |  |  | N/A | N/A | Normal | To be decommissioned
R4WAPPP130(HongKong-Svr-M4) | 10.82.32.174 | NHK---HONGKONG-SVR-M4 Asset Management System | to be migration | Yes | #N/A | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*1 | 2 | 40/40/40 | Windows Server 2008 R2 Standard | EM7/SCOM | NHK | NHK7 | Tim Wu | 1 |  | Tony.Wu@nike.com | Asia | Normal
R4WAPPP131 | 10.82.32.182 | LAMS （Local Attribute Management System） | to be migration | Yes | NotApplicable | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*4 | 32 | 80/500 | Windows Server 2012 R2 Standard | EM7/SCOM | LAMS | LAMS | David Yin | 2 |  | Iven.Zhang@nike.com/Jason.Ding@nike.com | China Only | Normal
R4WAPPP133 | 10.82.32.177 | Converse-Baymark DB Server | to be migration | Yes | NotApplicable | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*8 | 32 | 60/1500/50/1024 | Windows Server 2008 R2 Standard | EM7/SCOM | Converse | Converse Raymark | Tim Wu | 2 |  | Converse RayMark Team(Jacky.chen@converse.com) | China Only | Normal
R4WAPPP134 | 10.82.32.206 | Hyperion Gateway server | to be migration | Yes | NotApplicable | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*4 | 16 | 80/80/160 | Windows Server 2012 R2 Standard | EM7/SCOM | Hyperion Gateway server | Hyperion Gateway server | Jim Wang | 1 |  | Joan.Fernandez@nike.com | Asia | Normal
R4WAPPP135 | 10.82.32.207 | SIM Server | to be migration | Yes | NotApplicable | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*2 | 4 | 80/80 | Windows Server 2012 R2 Standard | EM7/SCOM | SIM | SIM | David Yin | 1 |  | SIM Team | Asia | Normal
R4WAPPP138 | 10.82.32.197 | blank Server , to be shutdown | to be shutdown | Yes | NotApplicable | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*2 | 8 | 120/80 | Windows Server 2012 R2 Standard | EM7/SCOM |  | N/A | N/A |  |  | N/A | N/A | Normal | To be decommissioned
R4WAPPP139 | 10.82.32.184 | TM1 client | to be migration | Yes | NotApplicable | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*4 | 8 | 80/40/40 | Windows Server 2012 R2 Standard | EM7/SCOM | TM1 | TM1 | Rongwei | 1 |  | Adam.Tang2@nike.com/Lily.He@nike.com | Asia | Normal
R4WAPPP140 | 10.82.32.196 | RICOH follow ME equitrac license server | to be migration | Yes | NotApplicable | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*2 | 8 | 80/100 | Windows Server 2012 R2 Standard | EM7/SCOM | RICOH follow ME | Follow Me print | Jimmy | 1 | 5 | Bharath.Venkatesh@nike.com | Asia | Normal | Printer server should be kept in local
R4WAPPP141 | 10.82.32.113 | RICOH follow ME FollowMe printing - Equitrac | to be migration | Yes | NotApplicable | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*2 | 8 | 80/100 | Windows Server 2012 R2 Standard | EM7/SCOM | RICOH follow ME | Follow Me print | Jimmy | 1 | 5 | Bharath.Venkatesh@nike.com | Asia | Normal | Printer server should be kept in local
R4WAPPP142 | 10.82.32.113 | Converse Data Warehouse server and ETL server | to be migration | Yes | NotApplicable | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*2 | 64 | 80/900/320/50 | Windows Server 2012 R2 Standard | EM7/SCOM | Converse | Converse3 | Tim Wu | 1 |  | stanly.wang@converse.com/Xu.Li@converse.com | China Only | High on CPU or memory
R4WAPPP143 | 10.82.32.115 | Converse Integrated Data Foundation & Analytics data warehouse | to be migration | Yes | NotApplicable | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*4 | 16 | 80/300/120/500 | Windows Server 2012 R2 Standard | EM7/SCOM | Converse | Converse4 | Tim Wu | 1 |  | stanly.wang@converse.com/Xu.Li@converse.com | China Only | Normal
R4WAPPP145 | 10.82.32.137 | SolarWinds polling | to be migration | Yes | NotApplicable | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*2 | 8 | 80/150 | Windows Server 2012 R2 Standard | EM7/SCOM | SolarWinds | SolarWinds | MaoYan/Tim Ni | 2 |  | Steve.Johnston@nike.com/Valjean.Clark@nike.com | Asia | Normal
R4WAPPP146 | 10.82.32.158 | SolarWinds | to be migration | Yes | NotApplicable | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*2 | 16 | 80/150 | Windows Server 2012 R2 Standard | EM7/SCOM | SolarWinds | SolarWinds | MaoYan/Tim Ni | 2 |  | Steve.Johnston@nike.com/Valjean.Clark@nike.com | Asia | Normal
R4WCASP001(SINWPEP1WDFS001) | 10.82.32.156 | Casper Server | to be migration | Yes | #N/A | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*4 | 8 | 80/350 | Windows Server 2012 R2 Standard | EM7/SCOM | Casper | Casper | Tim Ni | 1 |  | Shawn Cavagnaro / Brad Biehl | Asia | Normal
R4WCASP002(SINEUSP1WSCCM01) | 10.82.32.157 | Casper Server | to be migration | Yes | #N/A | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*4 | 8 | 80/350 | Windows Server 2012 R2 Standard | EM7/SCOM | Casper | Casper | Tim Ni | 1 |  | SCCM Team/Lst-CDT.Retail.SCCM@nike.com | Asia | Normal
R4WCCMP001 | 10.82.32.34 | SC Configuration Manager DP | to be migration | Yes | Normal | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*2 | 8 | 80/200 | Windows Server 2012 R2 Standard | EM7/SCOM | SCCM | SCCM | Yu Xun/Jim Wang | 4 |  | SCCM Team/Lst-CDT.Retail.SCCM@nike.com | Asia | Normal
R4WCCMP002 | 10.82.48.62 | SC Configuration Manager DP | to be migration | Yes | NotApplicable | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*2 | 8 | 80/200 | Windows Server 2012 R2 Standard | EM7/SCOM | SCCM | SCCM | Yu Xun/Jim Wang | 4 |  | SCCM Team/Lst-CDT.Retail.SCCM@nike.com | Asia | Normal
R4WMDBP001 | 10.82.32.183 | LAMS-Mongo DB server | to be migration | Yes | NotApplicable | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*4 | 64 | 80/500 | Windows Server 2012 R2 Standard | EM7/SCOM | LAMS | LAMS | David Yin | 2 |  | Iven.Zhang@nike.com/Jason.Ding@nike.com | Asia | High on CPU or memory
R4WRDSP001 | 10.82.32.30 | Jump Server 1 (Infrastructure) | to be shutdown | Yes | NotApplicable | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*1 | 8 | 80/40 | Windows Server 2012 R2 Standard | EM7/SCOM | Jump Server | N/A | N/A |  |  | Windows team | Asia | Normal | Jump server
R4WRDSP002 | 10.82.32.31 | Jump Server 2 (Application - GSS) | to be shutdown | Yes | Normal | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*1 | 8 | 80/40 | Windows Server 2012 R2 Standard | EM7/SCOM | Jump Server | N/A | N/A |  |  | Windows team | Asia | Normal | Jump server
R4WRDSP003 | 10.82.32.32 | Jump Server 3 (Application - BI) | to be shutdown | Yes | Normal | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*1 | 8 | 80/40 | Windows Server 2012 R2 Standard | EM7/SCOM | Jump Server | N/A | N/A |  |  | Windows team | Asia | Normal | Jump server
R4WRDSP004 | 10.82.48.64 | Jump Server | to be shutdown | Yes | NotApplicable | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*2 | 8 | 80 | Windows Server 2012 R2 Standard | EM7/SCOM | Jump Server | N/A | N/A |  |  | Windows team | Asia | Normal | Jump server
R4WRDSP005 | 10.82.32.86 | Jump Server (service desk) | to be shutdown | Yes | NotApplicable | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*4 | 12 | 80/100 | Windows Server 2012 R2 Standard | EM7/SCOM | Jump Server | N/A | N/A |  |  | Windows team | Asia | Normal | Jump server
R4WVMMP001 | 10.82.48.63 | SC Virtual Machine Manager | to be shutdown | Yes | Critical | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*16 | 32 | 80/200/200 | Windows Server 2012 R2 Standard | EM7/SCOM | SC Virtual Machine Manager | N/A | N/A |  |  | Windows team | Asia | Normal
SGCISP1DLP01 | 10.82.32.202 | Data Loss Protection server. | to be migration | Yes | NotApplicable | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*4 | 16 | 80/240 | Windows Server 2012 R2 Standard | EM7/SCOM | SG CIS | CIS DLP | Jimmy/Rongwei | 3 |  | CIS team/Lst-Technology.CIS.STM.NetworkTech@nike.com | Asia | Normal
SGCISP1DLP02 | 10.82.32.203 | Data Loss Protection server. | to be migration | Yes | NotApplicable | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*4 | 16 | 80/240 | Windows Server 2012 R2 Standard | EM7/SCOM | SG CIS | CIS DLP | Jimmy/Rongwei | 3 |  | CIS team/Lst-Technology.CIS.STM.NetworkTech@nike.com | Asia | Normal
SGCISP1EPO01 | 10.82.32.204 | ePO server. | to be migration | Yes | NotApplicable | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*2 | 4 | 80/20 | Windows Server 2012 R2 Standard | EM7/SCOM | SG CIS | CIS EPO | Jimmy/Rongwei | 3 |  | CIS team/Lst-Technology.CIS.STM.NetworkTech@nike.com | Asia | Normal
SGCISP1WTRIDB1 | 10.82.32.201 | SQL Server for Websense Triton. | to be migration | Yes | NotApplicable | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*4 | 16 | 80/240/240 | Windows Server 2012 R2 Standard | EM7/SCOM | SG CIS | CIS Websense SQL | Jimmy/Rongwei | 3 |  | CIS team/Lst-Technology.CIS.STM.NetworkTech@nike.com | Asia | Normal
SINADSP1WADC001 | 10.82.32.104 | Domain controller for ad.nike.com | to be confimed | Yes | #N/A | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*8 | 16 | 80/40/200 | Windows Server 2012 R2 Standard | EM7/SCOM | Domain controller | AD | Terry/Jimmy | 1 | 5 | AD team | Asia | Normal
SINADSP1WADC002 | 10.82.32.20 | Domain controller for ad.nike.com | to be confimed | Yes | NotApplicable | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*8 | 16 | 80/40 | Windows Server 2012 R2 Standard | EM7/SCOM | Domain controller | AD | Terry/Jimmy | 1 | 5 | AD team | Asia | Normal
SHAEUSP1WSCCM49 | 10.82.32.112 | SCCM Server | to be migration | Yes | NotApplicable | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*4 | 8 | 80/900 | Windows Server 2012 R2 Standard | EM7/SCOM | SCCM | SCCM | Yu Xun/Jim Wang | 4 |  | SCCM Team/Lst-CDT.Retail.SCCM@nike.com | Asia | Normal
SINADSP1WARS001 | 10.82.32.151 | ActiveRole Server | to be confimed | Yes | NotApplicable | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*4 | 12 | 80/150/80 | Windows Server 2012 R2 Standard | EM7/SCOM | AD | AD | Terry/Jimmy | 1 | 5 | AD team | Asia | Normal
SINBISP1WCOG01 | 10.82.32.133 | IDP/VIP Portal/Giveaway/Format Conversion(HONGKONG-SVR-J5) | to be migration | Yes | NotApplicable | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*4 | 48 | 80/250/400/100 | Windows Server 2012 R2 Standard | EM7/SCOM | NHK | NHK8 | Tim Wu | 1 |  | Tony.Wu@nike.com | Asia | Normal
SINBISQ1WCOG01 | 10.82.36.57 | NHK DB | to be migration | Yes | NotApplicable | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*2 | 32 | 80/80/20/200 | Windows Server 2012 R2 Standard | EM7/SCOM | NHK | NHK9 | Tim Wu | 1 |  | Tony.Wu@nike.com | Asia | High in IO and throughput
SINBIST1WSQL001 | 10.82.36.63 | to be shutdown | to be shutdown | Yes | #N/A | Stopped | Intel Xeon CPU E5-2699 V3 2.30GHz*2 | 8 | 80/600/500 | Windows Server 2012 R2 Standard | EM7/SCOM | SEA | N/A | N/A |  |  | To be confirmed | Asia | Normal | To be decommissioned
SINCTXP1WXFM002 | 10.82.32.159 | secondard Broken server in SGDC (as Fm005) | to be migration | Yes | NotApplicable | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*2 | 4 | 80 | Windows Server 2012 R2 Standard | EM7/SCOM | Citrix | Citrix | George Liu | 2 |  | Crtrix Team | Asia | Normal
SINCTXP1WXFM004 | 10.82.32.224 | secondardVDA (for Raymark application) server in SGDC (as Fm005) | to be migration | Yes | NotApplicable | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*4 | 32 | 80/100 | Windows Server 2012 R2 Standard | EM7/SCOM | Citrix | Citrix | George Liu | 2 |  | Crtrix Team | Asia | High on CPU or memory
SINEBRP1WCVMA01 | 10.82.32.143 | Backup Server | to be confimed | Yes | NotApplicable | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*12 | 48 | 80/500/600 | Windows Server 2012 R2 Standard | EM7/SCOM | Commvault | Commvault | Shayne/David Yin | 2 | 5 | Backup team | Asia | High on CPU or memory
SINEBRP1WCVMA02 | 10.82.32.144 | Backup Server | to be confimed | Yes | NotApplicable | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*12 | 48 | 80/500/600 | Windows Server 2012 R2 Standard | EM7/SCOM | Commvault | Commvault | Shayne/David Yin | 2 | 5 | Backup team | Asia | High on CPU or memory
SINEBRP1WCVMA21 | 10.82.32.185 | Commvault media agent | to be confimed | Yes | NotApplicable | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*12 | 48 | 80/500/600 | Windows Server 2012 R2 Standard | EM7/SCOM | Commvault | Commvault | Shayne/David Yin | 2 | 5 | Backup team | Asia | High on CPU or memory
SINEBRP1WCVMA22 | 10.82.32.186 | Commvault media agent | to be confimed | Yes | NotApplicable | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*12 | 48 | 80/500/600 | Windows Server 2012 R2 Standard | EM7/SCOM | Commvault | Commvault | Shayne/David Yin | 2 | 5 | Backup team | Asia | High on CPU or memory
SINEUSP1WSCCM02 | 10.82.32.233 | SMS SQL Server | to be migration | Yes | NotApplicable | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*8 | 72 | 80 | Windows Server 2012 R2 Standard | EM7/SCOM | SCCM | SCCM | Yu Xun/Jim Wang | 4 |  | SCCM Team/Lst-CDT.Retail.SCCM@nike.com | Asia | Normal
SINEUSP1WSCCM03 | 10.82.32.234 | SMS Management Point/SMS Notification Server/SMS Software Update Point | to be migration | Yes | NotApplicable | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*8 | 16 | 80 | Windows Server 2012 R2 Standard | EM7/SCOM | SCCM | SCCM | Yu Xun/Jim Wang | 4 |  | SCCM Team/Lst-CDT.Retail.SCCM@nike.com | Asia | Normal
SINEUSP1WSCCM04 | 10.82.32.111 | SCCM Server | to be migration | Yes | NotApplicable | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*2 | 8 | 80/150/800 | Windows Server 2012 R2 Standard | EM7/SCOM | SCCM | SCCM | Yu Xun/Jim Wang | 4 |  | SCCM Team/Lst-CDT.Retail.SCCM@nike.com | Asia | Normal
SINNETP1WCMLOG1 | 10.82.32.110 | to be shutdown | to be shutdown | Yes | NotApplicable | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*2 | 8 | 80/500 | Windows Server 2012 R2 Standard | EM7/SCOM |  | N/A | N/A |  |  | To be confirmed |  | Normal | To be decommissioned
SINSHRP1WSQL01 | 10.82.32.125 | NHK Share DB | to be migration | Yes | Critical | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*12 | 32 | 80/200/500/20/10/20/10/10/5/10/5/20/10/100/200/200 | Windows Server 2012 R2 Standard | EM7/SCOM | NHK | NHK10 | Tim Wu | 1 |  | Tony.Wu@nike.com | Asia | High in IO and throughput

## Hyper-V QA
Hostname | IP Address | Role | In Scope | VM | Status | CPU | Memory（G） | Disk（G） | OS | Monitor | Classifications | Container | Migration owner | For Asia or China only | Performance Level | APP owner | Comments
R4WAPPQ002 | 10.82.36.41 | Application Server (China_BI_DEV) | Out of scope | Yes | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*1 | 8 | 40 | Windows Server 2012 R2 Standard | [7 empty] | Already in Azure
R4WAPPQ003 | 10.82.36.42 | Application Server (China_BI_QA) | Out of scope | Yes | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*4 | 16 | 40 | Windows Server 2012 R2 Standard | [7 empty] | Already in Azure
R4WAPPQ004 | 10.82.36.43 | Application Server (China_BI_QA) | Out of scope | Yes | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*2 | 32 | 80/301/301 | Windows Server 2012 R2 Standard | [7 empty] | Already in Azure
R4WAPPQ005 | 10.82.36.44 | Application Server (China_BI_DEV) | Out of scope | Yes | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*8 | 16 | 80 | Windows Server 2012 R2 Standard | [7 empty] | Already in Azure
R4WAPPQ006 | 10.82.36.45 | Application Server (China_BI_QA) | Out of scope | Yes | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*8 | 32 | 80/300/301 | Windows Server 2012 R2 Standard | [7 empty] | Already in Azure
R4WAPPQ007 | 10.82.36.46 | request by Jim | Out of scope | Yes | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*2 | 8 | 80/400 | Windows Server 2012 R2 Standard | [6 empty] | fran.yang@nike.com | Already in Azure
R4WAPPQ008 | 10.82.36.47 | request by George(GCHQ network team test server) | Out of scope | Yes | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*1 | 4 | 80/100 | Windows Server 2012 R2 Standard | [6 empty] | yan.mao@nike.com | Already in Azure
R4WAPPQ009 | 10.82.36.48 | wholesale BI migration project | Out of scope | Yes | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*2 | 8 | 80/1000/500/1000 | Windows Server 2012 R2 Standard | [7 empty] | Already in Azure
R4WAPPQ010 | 10.82.36.49 | wholesale BI migration project | Out of scope | Yes | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*8 | 64 | 80/500/100/500 | Windows Server 2012 R2 Standard | [7 empty] | Already in Azure
R4WAPPQ011 | 10.82.36.50 | wholesale BI migration project | Out of scope | Yes | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*4 | 64 | 80/1000/500 | Windows Server 2012 R2 Standard | [7 empty] | Already in Azure
R4WAPPQ012 | 10.82.36.51 | wholesale BI migration project | Out of scope | Yes | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*4 | 32 | 80/500/500 | Windows Server 2012 R2 Standard | [7 empty] | Already in Azure
R4WAPPQ013 | 10.82.36.52 | Wholesale BI target server | In scope | Yes | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*16 | 64 | 80/1000/500/1000/1000/500/1000/2048/1000 | Windows Server 2012 R2 Standard | EM7/SCOM | Wholesale BI |  |  | China | High on CPU or memory | Mark.Zhou@nike.com | Already in Azure
R4WAPPQ014 | 10.82.36.53 | Wholesale BI target server | In scope | Yes | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*8 | 64 | 80/1000/1000/1000/1000/1000/1000 | Windows Server 2012 R2 Standard | EM7/SCOM | Wholesale BI |  |  | China | High on CPU or memory | Mark.Zhou@nike.com | Already in Azure
R4WAPPQ016 | 10.82.36.55 | Converse Xpert, XEIS（shutdown） | Out of scope | Yes | Stopped | Intel Xeon CPU E5-2699 V3 2.30GHz*4 | 32 | 80/100 | Windows Server 2012 R2 Standard | EM7/SCOM | [5 empty] | Merlin.Mei@converse.com | Already in Azure
R4WAPPQ017 | 10.82.36.56 | Converse Xpert, XEIS（shutdown） | Out of scope | Yes | Stopped | Intel Xeon CPU E5-2699 V3 2.30GHz*8 | 32 | 80/1000/500 | Windows Server 2012 R2 Standard | EM7/SCOM | [5 empty] | Merlin.Mei@converse.com | Already in Azure
R4WAPPQ019 | 10.82.36.58 | BI---Non-Prod for tableau sandbox | Out of scope | Yes | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*2 | 4 | 80/100 | Windows Server 2012 R2 Standard | EM7/SCOM | [6 empty] | Already in Azure
R4WAPPQ020 | 10.82.36.59 | Tim Converse BI Test | Out of scope | Yes | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*4 | 64 | 80/500/500 | Windows Server 2012 R2 Standard | EM7/SCOM | [5 empty] | Kyle.Chen@converse.com | Already in Azure
R4WAPPQ021 | 10.82.36.60 | Tim Converse BI Test | Out of scope | Yes | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*2 | 12 | 80/200 | Windows Server 2012 R2 Standard | EM7/SCOM | [5 empty] | Kyle.Chen@converse.com | Already in Azure
R4WAPPQ022 | 10.82.36.61 | Tim Converse BI Test | Out of scope | Yes | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*1 | 4 | 80 | Windows Server 2012 R2 Standard | EM7/SCOM | [5 empty] | Kyle.Chen@converse.com | Already in Azure
R4WAPPQ024 | 10.82.36.63 | Tyler（Singapore backup）(Shutdown) | Out of scope | Yes | Stopped | Intel Xeon CPU E5-2699 V3 2.30GHz*1 | 4 | 80 | Windows Server 2012 R2 Standard | EM7/SCOM | [6 empty] | Already in Azure
R4WAPPQ025 | 10.82.36.64 | Yongyou Project QA server | Out of scope | Yes | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*4 | 16 | 80/1023 | Windows Server 2012 R2 Standard | EM7/SCOM | [6 empty] | Already in Azure
R4WAPPQ026 | 10.82.36.65 | Tyler（Singapore backup/1 TB CIFS share ） | Out of scope | Yes | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*1 | 4 | 80 | Windows Server 2012 R2 Standard | EM7/SCOM | [6 empty] | Already in Azure
R4WAPPQ027 | 10.82.36.66 | Tyler（Backup Team test client） | Out of scope | Yes | Running | Intel Xeon CPU E5-2699 V3 2.30GHz*1 | 4 | 80 | Windows Server 2012 R2 Standard | EM7/SCOM | [6 empty] | Already in Azure
R4WAPPQ028 | 10.82.36.67 | Tyler（Backup Team test client）(Shutdown) | Out of scope | Yes | Stopped | Intel Xeon CPU E5-2699 V3 2.30GHz*1 | 4 | 80 | Windows Server 2012 R2 Standard | EM7/SCOM | [6 empty] | Already in Azure
R4WSQLQ001 | 10.82.32.36 | test for R4WCLSP001 | Out of scope | Yes | Stopped | Intel Xeon CPU E5-2699 V3 2.30GHz*4 | 16 | 270 | Windows Server 2012 R2 Standard | EM7/SCOM | SQL cluster |  |  | China | Normal | Lst-digitaltech.CognizantMsSQL.DBA | To be decommissioned

## VMware
Name | IP Address | Role | vCPU | Memory (GB) | Disk Space (GB) | vNic | Hardware Version | Application/Service | For Asia or China only | Performance Level | OS | Monitor | APP Owner | Comments
EUSP1WSCCMP01 | 10.82.32.237 | SCCM | 4 | 8 | 1130 | 1 | vmx-11 | SCCM | Asia | Normal | Microsoft Windows Server 2012 (64-bit) | EM7/SCOM | SCCM team
EUSP1WSCCMP02 | 10.82.32.238 | SCCM | 4 | 8 | 1130 | 1 | vmx-11 | SCCM | Asia | Normal | Microsoft Windows Server 2012 (64-bit) | EM7/SCOM | SCCM team
HK-SITP1WSTHDB1 | 10.82.32.216 | ? | 8 | 64 | 2724 | 1 | vmx-10 |  |  |  | Microsoft Windows Server 2012 (64-bit) | EM7/SCOM | ?
HONGKONG-SVR-23 | 10.82.51.21 | NHK B2B Server | 2 | 16 | 380 | 1 | vmx-10 | NHK | Asia | Normal | Microsoft Windows Server 2012 (64-bit) | EM7/SCOM | Tony Wu
HONGKONG-SVR-41 | 10.82.32.215 | SEA Biz Report Server - iMFT (VM) + Schudule Task Jobs | 8 | 8 | 280 | 1 | vmx-10 | SEA | Asia | Normal | Microsoft Windows Server 2008 R2 (64-bit) | EM7/SCOM | Prasanth Soman
HONGKONG-SVR-43 | 10.82.32.211 | ORACLE DBs (POS report) server for SEA + Schudule Task Jobs | 2 | 4 | 240 | 1 | vmx-10 | SEA | Asia | Normal | Microsoft Windows Server 2008 R2 (64-bit) | EM7/SCOM | Prasanth Soman
HONGKONG-SVR-S9 | 10.82.32.199 | SQL-SQL Server -Test - server owner Andrew Solow (Hurley) | 2 | 4 | 370.01 | 1 | vmx-10 | MS SQL（Hurley） | Asia | Normal | Microsoft Windows Server 2003 Standard (32-bit) | EM7/SCOM | Andrew Solow
Jump Host temp | 10.82.52.21 | jump host | 2 | 4 | 80 | 1 | vmx-11 |  |  |  | Microsoft Windows Server 2012 (64-bit) | EM7/SCOM
NKE-WIN-APP-P49 | 10.82.32.214 | Schudule Tasks + Oracle Client for ODBC Server | 4 | 8 | 160 | 1 | vmx-08 | SEA | Asia | Normal | Microsoft Windows Server 2012 (64-bit) | EM7/SCOM | SEA - Jun Sun
NKE-WIN-SCM-P44 | 10.82.32.230 | SCCM | 4 | 8 | 825 | 1 | vmx-08 | SCCM | Asia | Normal | Microsoft Windows Server 2008 R2 (64-bit) | EM7/SCOM | SCCM team
NKE-WIN-SCM-P49 | 10.82.32.231 | SCCM | 4 | 8 | 830 | 1 | vmx-10 | SCCM | Asia | Normal | Microsoft Windows Server 2008 R2 (64-bit) | EM7/SCOM | SCCM team
NKE-WIN-SEA-P02 | 10.82.32.210 | Schudule Tasks + SEA POS Log report server | 2 | 4 | 180 | 1 | vmx-10 | SEA | Asia | Normal | Microsoft Windows Server 2012 (64-bit) | EM7/SCOM | Prasanth Soman/SEA - Jun Sun
R4WAPPP137 | 10.82.32.123 | RTGCGSSAPP | 2 | 4 | 230 | 1 | vmx-11 |  |  |  | Microsoft Windows Server 2012 (64-bit) | EM7/SCOM | ?
SHAEUSP1WSCCM44 | 10.82.32.235 | SCCM | 4 | 8 | 1580 | 1 | vmx-11 | SCCM | Asia | Normal | Microsoft Windows Server 2012 (64-bit) | EM7/SCOM | SCCM team
SINADSP1WWNS002 | 10.82.32.241 | WINS | 2 | 4 | 80 | 1 | vmx-11 | WINS | Asia | Normal | Microsoft Windows Server 2012 (64-bit) | EM7/SCOM | WINS team
SINCSCP1WCIAPP1 | 10.82.51.27 | CSC | 4 | 8 | 200 | 1 | vmx-11 |  |  |  | Microsoft Windows Server 2012 (64-bit) | EM7/SCOM | ?
SINCTXP1WXFM001 | 10.82.32.200 | Citrix | 2 | 8 | 200 | 1 | vmx-10 | Citrix | Asia | Normal | Microsoft Windows Server 2003 Standard (32-bit) | EM7/SCOM | Crtrix team
SINIAPP1WDMZ01 | 10.82.51.23 | Niketracking.com | 2 | 8 | 80 | 1 | vmx-11 | Web site | Asia | Normal | Microsoft Windows Server 2012 (64-bit) | EM7/SCOM | Chen, Madge <Madge.Chen@nike.com>
SINIAPP1WDMZ02 | 10.82.51.24 | Korea E-Tax System | 2 | 4 | 280 | 1 | vmx-11 | Web site | Asia | Normal | Microsoft Windows Server 2012 (64-bit) | EM7/SCOM | Chen, Madge <Madge.Chen@nike.com>
SINIAPP1WDMZ03 | 10.82.51.25 | SampleSale and panorama photo web | 4 | 8 | 120 | 1 | vmx-11 | Web site | China Only | Normal | Microsoft Windows Server 2012 (64-bit) | EM7/SCOM | Chen, Madge <Madge.Chen@nike.com>
SINIAPP1WDMZ04 | 10.82.51.26 | Converse BI web sitre | 2 | 4 | 180 | 1 | vmx-11 | Web site | China Only | Normal | Microsoft Windows Server 2012 (64-bit) | EM7/SCOM | Stanly.Wang@converse.com
SINSGWAPPP002 | 10.82.32.218 | SCCM Primary Stie/FSP | 4 | 4 | 400 | 1 | vmx-11 | SCCM | Asia | Normal | Microsoft Windows Server 2012 (64-bit) | EM7/SCOM | SCCM team
SINSGWAPPP003 | 10.82.32.219 | SCCM Primary SQL | 4 | 4 | 400 | 1 | vmx-11 | SCCM | Asia | Normal | Microsoft Windows Server 2012 (64-bit) | EM7/SCOM | SCCM team
SINSGWAPPP004 | 10.82.32.220 | SCCM Primary MP/Primary SUP | 4 | 4 | 400 | 1 | vmx-11 | SCCM | Asia | Normal | Microsoft Windows Server 2012 (64-bit) | EM7/SCOM | SCCM team
test70 | 10.82.32.15 | ? | 2 | 4 | 80 | 1 | vmx-11 |  |  |  | Microsoft Windows Server 2012 (64-bit) | EM7/SCOM | ?
Win12R2 | power off | Template | 2 | 4 | 80 | 1 | vmx-11 |  |  |  | Microsoft Windows Server 2012 (64-bit) | EM7/SCOM
Win2008 | 10.82.60.206 | Template | 2 | 4 | 120 | 1 | vmx-11 |  |  |  | Microsoft Windows Server 2008 (32-bit) | EM7/SCOM

## Sheet1
FollowUps | (Multiple Items)
Row Labels | Count of Hostname
1 | 39
2 | 41
3 | 9
4 | 11
5 | 21
TBD | 2
Grand Total | 123

## VMWare VM list (hidden)
Name | Role | Guest OS | IP Address | APP owner | Comments
HK-NHKP1LNHKRPT |  | Red Hat Enterprise Linux 6 (64-bit) | 10.82.33.58
HONGKONG-SVR-23 |  | Microsoft Windows Server 2012 (64-bit) | 10.82.51.21
HONGKONG-SVR-S9 |  | Microsoft Windows Server 2003 Standard (32-bit) | 10.82.32.199
Jump Host temp | jump host | Microsoft Windows Server 2012 (64-bit) | 10.82.52.21
nike-sdcs |  | Red Hat Enterprise Linux 7 (64-bit) | 10.82.51.100
NKE-LNX-HKG-P003 |  | Red Hat Enterprise Linux 6 (64-bit) | 10.82.32.208
NKE-LNX-HKG-Q003 |  | Red Hat Enterprise Linux 6 (64-bit) | 10.82.32.209
NKE-WIN-SCM-P22 | SCCM | Microsoft Windows Server 2008 R2 (64-bit) | 10.82.32.225
NKE-WIN-SCM-P23 | SCCM | Microsoft Windows Server 2008 R2 (64-bit) | 10.82.32.226
NKE-WIN-SCM-P24 | SCCM | Microsoft Windows Server 2008 R2 (64-bit) | 10.82.32.227
NKE-WIN-SCM-P42 | SCCM | Microsoft Windows Server 2008 R2 (64-bit) | 10.82.32.228
NKE-WIN-SCM-P43 | SCCM | Microsoft Windows Server 2008 R2 (64-bit) | 10.82.32.229
NKE-WIN-SCM-P44 | SCCM | Microsoft Windows Server 2008 R2 (64-bit) | 10.82.32.230
NKE-WIN-SCM-P49 | SCCM | Microsoft Windows Server 2008 R2 (64-bit) | 10.82.32.231
ora01-p-sin.nike.com |  | Red Hat Enterprise Linux 6 (64-bit) | 10.82.33.64
R4WAPPP137 |  | Microsoft Windows Server 2012 (64-bit) | 10.82.32.123
sd1-p-sin-mnode |  | Ubuntu Linux (64-bit) | 10.82.58.12
sgcisp1lrp7000 |  | Red Hat Enterprise Linux 7 (64-bit) | 10.82.33.61
sgcisp1lrp7010 |  | Red Hat Enterprise Linux 7 (64-bit) | 10.82.33.62
SGCISP1NLE01 |  | Red Hat Enterprise Linux 7 (64-bit) | 10.82.33.59
SGCISP1NLE02 |  | Red Hat Enterprise Linux 7 (64-bit) | 10.82.33.60
SGDC-SVR-H1 |  | Microsoft Windows Server 2008 R2 (64-bit) | 10.82.32.198
SINCISP1LCPPM01 | CIS | CentOS 4/5/6/7 (64-bit) | 10.82.33.41
SINCISP1LCPPM02 | CIS | CentOS 4/5/6/7 (64-bit) | 10.82.33.42
SINCISP1LCPPM03 | CIS | CentOS 4/5/6/7 (64-bit) | 10.82.33.43
SINCISP1LCPPM04 | CIS | CentOS 4/5/6/7 (64-bit) | 10.82.33.44
SINCSCP1WCIAPP1 | CSC | Microsoft Windows Server 2012 (64-bit) | 10.82.51.27
SINCTXP1WXFM001 | Citrix | Microsoft Windows Server 2003 Standard (32-bit) | 10.82.32.200
SINDNSP1AAUTH01 | DNS Blue Cat | Ubuntu Linux (64-bit) | 10.82.33.160
SINDNSP1ACACP01 | DNS Blue Cat | Ubuntu Linux (64-bit) | 10.82.33.162
SINDNSP1ACACS01 | DNS Blue Cat | Ubuntu Linux (64-bit) | 10.82.33.161
SINDNSP1ACACX01 | DNS Blue Cat | Ubuntu Linux (64-bit) | 10.82.33.163
SINDNSP1ADHFO01 | DNS Blue Cat | Ubuntu Linux (64-bit) | 10.248.12.12
SINDNSP1ADHFO02 | DNS Blue Cat | Ubuntu Linux (64-bit) | 10.248.12.28
SINEUSP1ABOMAA1 |  | Red Hat Enterprise Linux 6 (64-bit) | 10.82.51.22
SINIAPP1WDMZ01 | DMZ | Microsoft Windows Server 2012 (64-bit) | 10.82.51.23
SINIAPP1WDMZ02 | DMZ | Microsoft Windows Server 2012 (64-bit) | 10.82.51.24
SINIAPP1WDMZ03 | DMZ | Microsoft Windows Server 2012 (64-bit) | 10.82.51.25
SINIAPP1WDMZ04 | DMZ | Microsoft Windows Server 2012 (64-bit) | 10.82.51.26
SINLPEP1LORA001 |  | Red Hat Enterprise Linux 5 (64-bit) | 10.82.32.193
SINMONP1ASCIL01 | Science Logic | Red Hat Enterprise Linux 5 (64-bit) | 10.82.33.49
SINMONP1ASCIL02 | Science Logic | Red Hat Enterprise Linux 5 (64-bit) | 10.82.33.50
SINMONP1ASCIL03 | Science Logic | Red Hat Enterprise Linux 5 (64-bit) | 10.82.33.51
SINMONP1ASCIL04 | Science Logic | Red Hat Enterprise Linux 5 (64-bit) | 10.82.33.52
SINMONP1ASCIL05 | Science Logic | Red Hat Enterprise Linux 5 (64-bit) | 10.82.33.53
SINMONP1ASCIL06 | Science Logic | Red Hat Enterprise Linux 5 (64-bit) | 10.82.33.54
SINMONP1ASCIL07 | Science Logic | Red Hat Enterprise Linux 5 (64-bit) | 10.82.33.55
SINMONP1ASCIL08 | Science Logic | Red Hat Enterprise Linux 5 (64-bit) | 10.82.33.56
SINMONP1ASCIL09 | Science Logic | Red Hat Enterprise Linux 5 (64-bit) | 10.82.33.57
SINNETP1AARWV01 | AirWave | Red Hat Enterprise Linux 6 (64-bit) | 10.82.33.45
SINNETP1AISE026 | ISE | Red Hat Enterprise Linux 6 (64-bit) | 10.82.54.11
SINNETP1AISE027 | ISE | Red Hat Enterprise Linux 6 (64-bit) | 10.82.54.12
SINNETP1AJNSP01 |  | Red Hat Enterprise Linux 5 (64-bit) | 10.82.33.47
SINNETP1AJNSP02 |  | Red Hat Enterprise Linux 5 (64-bit) | 10.82.33.48
SINSGWAPPP002 | WHQ Windows | Microsoft Windows Server 2012 (64-bit) | 10.82.32.218
SINSGWAPPP003 | WHQ Windows | Microsoft Windows Server 2012 (64-bit) | 10.82.32.219
SINSGWAPPP004 | WHQ Windows | Microsoft Windows Server 2012 (64-bit) | 10.82.32.220
SINWPEPM1WVRM01 |  | SUSE Linux Enterprise 11 (64-bit) | 10.82.32.205

## VM no VHD info (hidden)
Name
r4whvhp001
r4whvhp002
r4whvhp003
r4whvhp004
r4whvhp005
r4whvhp006
r4whvhp007
r4wclhp001
SINADSP1WADC001
r4wsqlp001
r4wsqlp002
r4wsqlp003
r4wclsp001
R4WSQLP-BI
R4WSQLP-ER
R4WSQLP-IR
R4WSQLP-XC
R4LSSHP001
R4WAPPP006
R4WAPPP007
R4WAPPP008
R4WAPPP009
R4WAPPP020
R4WAPPP021
R4WAPPP081
R4WAPPP089
R4WAPPP093
R4WAPPP099(SINEBRP1WCVMA01)
R4WAPPP100(SINEBRP1WCVMA02)
R4WAPPP104
R4WAPPP130(HongKong-Svr-M4)
R4WAPPQ015
R4WAPPQ018
R4WAPPQ023
R4WAPPQ028
R4WAPPQ029
R4WAPPQ030
R4WAPPQ031